# Project Plan & Launch Strategy

Book-a-Ride: Post-Venue-Booking Transportation Feature

| Project | Book-a-Ride — Transportation Feature for Playo |
| --- | --- |
| Document | Project Plan & Launch Strategy — Phase 1 & Phase 2 |
| Prepared By | Rajat Pratap Singh Gaur |
| Prepared For | Mentor Review |
| Date | 23 September 2026 |
| Status | Draft for Review |

# 1. Purpose

This plan lays out how Playo will roll out the Book-a-Ride feature in two phases — a low-cost manual pilot (Phase 1) followed by a fully automated MVP (Phase 2) — including timeline, milestones, team ownership, and the go/no-go gate between phases.

# 2. Overall Approach

- Phase 1 tests real demand cheaply, with no engineering investment in ride-booking infrastructure.

- Phase 2 only begins once Phase 1 data supports the business case (see Section 5, Go/No-Go Criteria).

- Each phase launches in one pilot city/sport first, then expands once results are validated.

# 3. Phase 1 Plan — Manual / Concierge Pilot (approx. 9 weeks)

| Timeline | Activity | Owner |
| --- | --- | --- |
| Week 1 | Finalize pilot city, sport, and vendor(s); align ops team on manual booking process. | Product + Ops |
| Week 2 | Build and test the in-app ride prompt, request capture, and WhatsApp confirmation flow (FR-101 to FR-105). | Engineering |
| Week 3 | Build cancellation/reschedule sync and the weekly logging report (FR-106 to FR-110). | Engineering + Ops |
| Week 4 | Internal dry run — team tests the full flow end-to-end with dummy bookings. | QA + Product |
| Week 5-8 | Live pilot in one city/sport; ops fulfils requests manually; weekly demand log reviewed. | Ops + Product |
| Week 9 | Analyze pilot data; go/no-go decision for Phase 2 based on request rate and fulfilment rate. | Product Leadership |

# 4. Phase 2 Plan — Automated MVP (approx. 12 weeks)

Starts only after a Go decision from Phase 1.

| Timeline | Activity | Owner |
| --- | --- | --- |
| Week 1-2 | Finalize and contract the ride-partner API (fare estimate, booking, tracking, payments). | Product + Legal |
| Week 3-5 | Build fare estimate, ride selection, and payment integration (FR-201 to FR-206a). | Engineering |
| Week 6-7 | Build booking confirmation, live tracking, and post-ride rating (FR-207 to FR-211). | Engineering |
| Week 8 | Build the ride-attach-rate measurement dashboard (FR-212). | Engineering + Analytics |
| Week 9 | QA across payment failure, no-driver, and cancellation edge cases. | QA |
| Week 10 | Soft launch in the Phase 1 pilot city; monitor completion rate and ratings closely. | Product + Ops |
| Week 11-12 | Expand to additional cities/sports based on soft-launch results. | Product Leadership |

# 5. Go / No-Go Criteria (Phase 1 → Phase 2)

- Healthy ride request rate as a % of eligible venue bookings during the pilot (BRD Section 7).

- Ops team can fulfil most requests without major delays or complaints.

- No major safety, liability, or user-trust issues surfaced during the pilot.

- Clear vendor/ride-partner options exist to support an automated Phase 2 integration.

# 6. Launch Strategy

## Phase 1 — Soft, Low-Visibility Launch

- Single city and sport only, kept intentionally small to manage manual ops load.

- No paid marketing — feature is discovered organically by users booking in the pilot city.

- Direct feedback loop with early users via WhatsApp to catch issues fast.

## Phase 2 — Phased Rollout

- Soft launch back in the Phase 1 city first, since ops and users there are already familiar with the feature.

- Monitor completion rate and ratings closely for the first 2 weeks before expanding.

- Expand city-by-city / sport-by-sport rather than a single big-bang national launch.

- Once stable, consider light in-app promotion (e.g. a banner) to boost ride attach rate.

# 7. Team & Ownership

| Role | Responsibility |
| --- | --- |
| Product Team | Owns timeline, requirements, and go/no-go decisions |
| Ops Team | Runs manual fulfilment in Phase 1; monitors service quality in Phase 2 |
| Engineering | Builds prompts, logging, and the Phase 2 ride-partner integration |
| QA | Tests edge cases — payment failures, no-driver, cancellations |
| Analytics | Builds and maintains the ride-attach-rate dashboard |

# 8. Key Risks to the Plan

- Phase 1 timeline depends on how fast a local cab vendor can be onboarded.

- Phase 2 timeline depends on the ride-partner's API readiness and contracting speed — largely outside Playo's control.

- Low pilot demand could delay or block the Phase 2 go-ahead (see BRD, Assumptions & Constraints).